PROCESS FOR RESEARCH PROJECTS

PHASE 1 – From idea to application, project proposal, tender submission

Contact a member of RIE if you require assistance in providing this description, preparing tender.

If you require assistance in the preparation of a costing, please complete the costing request form which can be found at http://www.gcu.ac.uk/rie/riedocuments/.  If you have any queries email rie.costings@gcu.ac.uk and a member of staff will contact you.  RIE operate on a 24 hour response rate when possible.

Commercial activity is recommended to make a 20% surplus.

PAF Form Risk Register are available at http://www.gcu.ac.uk/rie/riedocuments/ or contact RIE for assistance.

University standard terms and conditions are available.  If submitting a tender that has terms and conditions  specified at start of tendering process, contact RIE, Contracts Advisor as soon as possible for advice

Complete and sign PAF, (guidelines available at http://www.gcu.ac.uk/rie/riedocuments/  Contact RIE if you require assistance

RIE will read the paperwork, check and sign off costings and sign PAF

RIE will scan the full set of documentation, and send both you and your school a copy of the application documentation for your records. RIE will upload your documentation to PURE

RIE will submit consultancy / CPD proposals with draft contracts to clients.  RIE will assist with Contract Research Proposals.

RIE and School Research Advisors will liaise to take PAF through this process up to Dean’s signature. PAF will be returned to RIE by School Advisors.

Describe the proposed activity

Cost the activity, then agree price with client.

Prepare application, tender or project proposal and risk register.

Complete and sign university project approval form

Submit PAF, costing and Risk Register to School / Support Department for approval via Assistant Dean in School

Submit to RIE for approval

RIE submit to PVC (Research) for university authorisation (please allow 48 hours for this part of the process.

.

Applications, project proposals, tenders are now ready for submission this must match costs approved by University.

Submit to Dean of School for approval

RIE and School Advisors liaise to return signed PAF to RIE for submission to PVC Research

PAF PROCESS

PAF STEP BY STEP GUIDANCE

This information is used by RIE in the preparation of reports, as well as being the first step to an account being set up by the finance office (necessary for recruitment of staff, as well as invoicing)

RIE will liaise with the finance office with reference to the documentation required to enable them to set up an account, therefore it  is important that RIE receive as much information as possible e.g. breakdown of finance, how it will be paid, actual start and end date of project. Please contact a member of RIE if you have any queries.

Contact RIE on rie.costings@gcu.ac.uk and a member of staff will assist you with any revision of costings and PAF.

RIE will arrange this via the PVC (Research). Please note individuals must not sign on behalf of the university as this will nullify the formal agreement.  Only members of the Executive Board have legal authority.

RIE will send a signed copy of contract to client and copies will be sent to the principal investigator and the School for their records.

RIE will send all relevant documentation to the finance office. Documents will be uploaded to PURE.

Finance office will set up account for the financial management of the project. Contact ma@gcu.ac.uk if you have any queries.

As soon as you receive notification of the outcome of your proposal / tender / bid (whether successful or unsuccessful) – please notify RIE

Send letter of award and accompanying documentation, proposed contract or terms and conditions to RIE.

If the offer from the client differs from that originally documented on the PAF, RIE will advise if reauthorisation is required and will assist in amending PAF and contract

Formal signature of contract, acceptance of terms and conditions.  Client signature required also.

Contract process concluded paperwork sent to Finance.

PAF PROCESS

STEP BY STEP GUIDANCE

Consultancy and CPD contract will be drafted by RIE Contracts Advisor and sent to client via contact details on PAF - otherwise….

Contracts are drafted by RIE, unless using client contract or standard terms and conditions.  RIE will review any contracts provided and deal with any amendments with client on your behalf.

PHASE 2 – From outcome notification to project start