## Template Risk Register
GLASGOW CALEDONIAN UNIVERSITY |  |  | GCU Research and Project Risk Register Template Exemplar for PGR projects | [6 empty] | SCHOOL/DEPARTMENT
|  |  | Get an up to date copy of this form from: | www.gcu.ac.uk/staff/riskmanagement/ | [5 empty] | PROJECT NAME
PROJECT RISK REGISTER | [9 empty] | PROJECT VALUE (NOT REQUIRED FOR PGR project)
[10 empty] | OVERALL RESIDUAL PROJECT RISK |  |  |  | B
No. | SPECIFIC RISK |  |  | IMPACT (i.e. severity) | LIKELIHOOD | GROSS RISK SCORE AS PER MATRIX (1 - 16) | MITIGATION ACTIONS, PROCEDURES/CONTROLS IN PLACE | IMPACT (i.e. severity) | LIKELIHOOD | RESIDUAL RISK SCORE AS PER MATRIX (1 - 16) | 1. EARLY WARNING MECHANISMS 2. ACTIONS PLANNED | Timeline | Completed Actions | RISK OWNER
| Provide clear detail of the project risk, and then using the table below evaluate the impact and likelihood of this risk without any controls in place. |  |  | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List all mitigating actions, procedures and controls which will then impact on the gross risk score to create a revised residual risk score. | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List early warning mechanisms and other planned future actions which enhance the management of this risk, providing timelines where appropriate. | Key Milestone dates for any material events or actions planned | Note Actions completed since last Risk Register review | Name. Should be one individual
1 | The reputation of the University may be damaged if the project is not managed correctly. |  |  | Major | Possible | 8 | Where there is a possible risk to the reputation of the University a full management plan will be put in place to minimise the risk of exposure. This will include a plan for publicity and checking of all publicity material concerning the project. | Major | Unlikely | 4 | Where research findings are controversial a plan will be put in place to effectively prevent incorrect portrayal in the media. This will include a pro-active approach to publication of outcomes. | Initial plan Oct 2018 and ongoing review, 6 monthly March 2019, Oct 2019 | Completed Actions | Director of Studies (DoS)
2 | The number of participants required may not be recruited in a timely fashion. |  |  | Serious | Probable | 9 | Estimates of the rate at which participants can be recruited are based on previous research in this area. A set schedule has been developed. If recruitment falls behind the schedule additional actions are planned. | Serious | Possible | 6 | A clear timeline for recruitment will be established. This will have milestones which if not being met will trigger corrective action. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
3 | There is a risk of injury to the research team due to lone working and violence from research participant. |  |  | Major | Probable | 12 | A lone worker policy will be put in place. Where there is a risk of violence from participants against the researcher, working in pairs or alternative mitigation will be put in place in all cases. | Major | Unlikely | 4 | Participants will be assessed for risk of violence and appropriate measures put in place for each case. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
4 | There is a risk of researcher infection from participants. |  |  | Major | Possible | 8 | All local health and safety rules will be followed. This will include following best practice for prevention of spread of infection from participant to researcher. | Major | Unlikely | 4 | Signs and symptoms of any conditions will be known to the research and any indications of infection will immediately be notified to the appropriate medical professional. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
5 | There is a risk to the researcher of injury from chemical, mechanical or electrical causes during the routine conduct of research work. |  |  | Major | Probable | 12 | All local health and safety rules will be followed, including following recommended best practice for handling of chemicals and interaction with all mechanical and electrical equipment | Major | Unlikely | 4 | Prior to commencing all laboratory work a local risk assessment process will be conducted. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
6 | If the research work is not completed the external funder may not receive the expected outcomes from the project, leading to a poor relationship. |  |  | Serious | Unlikely | 3 | A clear time line has been established for project delivery and agreed with the funder. The schedule includes contingencies for slow progress and for unexpected minor delays in project delivery. | Serious | Unlikely | 3 | Discussions have been held with line managers to explore the possibility of having a contingency in place to cover any unexpected delays in project delivery. | Initial plan (date) and ongoing review (dates) |  | Director of Studies (DoS)
7 | If funding is withdrawn there is a risk the project cannot be delivered |  |  | Serious | Possible | 6 | Clear agreement has been reached with the funder as to what they are willing to fund and the conditions associated with this funding. If appropriate a contact has been signed. | Serious | Possible | 6 | A modification of the original plan has been developed which would allow project delivery, but to a slighly modified final end point. | Initial plan (date) and reaction to any funding change (dates) |  | Director of Studies (DoS)
8 | Ethical approval for the project may be delayed, potentially reducing the deliverables at the end of the project. Also there may be delays due to the necessity to gain approval to access participants via NHS R&D departments. |  |  | Serious | Certain | 12 | A realistic schedule has been planned, including a generous time for completion of ethical approval and accessing participants. Guidance has been sought from the R&D team and local clinical contacts concerning the requirements for ethical approval and accessing participants at the research site. | Serious | Possible | 6 | A schedule has been set which includes time periods for ethical approval and setting up access to research participants. This will be regularly reviewed to assess progress against objectives. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
9 | The participants taking part in the study may suffer injury or death as a results of taking part in the study |  |  | Major | Probable | 12 | Participants will only be asked to undertake procedures and processes that have previously been demonstrated to be safe. | Major | Possible | 8 | Ongoing monitoring of major complications that participants experience whilst registered participants in the research will be made. Any indication that procedures or processing being used are causing injury or death will immediately lead to suspension of the study. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
10 | Participants who are vulnerable (children, or those with limited capacity) will be taking part in the research potentially opening them up to exploitation by the research team. |  |  | Major | Possible | 8 | Where children are invovled in research or those with limited capacity carers/guardians will be engaged to give consent for participation and be present at all research data collection sessions. All research participants will have access to an independent named individual if they wish to discuss research procedures and processes. | Major | Unlikely | 4 | Any reports from participants or their carers of incorrect behaviour from researchers towards them will immediately result in suspesion of the project until further exploration of concerns has been made. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
11 | Loss of data security |  |  | Major | Possible | 8 | Hard copies of study data will be stored securely as per GCU guidelines. Data that may identify participants will be stored seperately from other study data. Electronic data will be stored securely as per GCU guidlelines. Access to study data will be limited to named researchers. | Major | Unlikely | 4 | Ensure all possible protections are in place at the start of the project and check periodically to ensure that data security has not been compromised. Liaise with the IT team in any instances of suspected or actual data security breach. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
12 | Researcher ill health/major life event |  |  | Major | Possible | 8 | Access to line manager and other GCU staff support services e.g. People Services, Occupational Health | Serious | Possible | 6 | Regular meetings of research student with supervisory team; identify other team member/s to take on some of the duties of the research student; Accessing GCU staff support services as required. | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
13 | Change of priorities |  |  | Significant | Possible | 4 | Adapt /include alternative plans to allow for change where needed | Minor | Possible | 2 | Meticulous planning and regular lab meetings of research supervisory team and student | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
14 | Equipment failure, hence delay of research timelines |  |  | Major | Possible | 8 | Accurate multi-user logs of usage kept on equipment. Alternative expts planned in event of delays to equipment repair. | Significant | Possible | 4 | Early identification of any problems with equipment by flagging up to research technicians | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
15 | Sample loss due to equipment damage (e.g. broken freezer) |  |  | Major | Possible | 8 | Maintain samples in freezers with back-up electrical supply, in case of power outage. | Serious | Possible | 6 | Back-up freezers have alarms fitted to allow transfer of samples to alternative freezers | Initial plan (date) and ongoing review (dates) |  | Research student (RS)
Impact
|  | 0 | Minor | Significant | Serious | Major
| Likelihood | Certain | 4 | 8 | 12 | 16
|  | Probable | 3 | 6 | 9 | 12
|  | Possible | 2 | 4 | 6 | 8
|  | Unlikely | 1 | 2 | 3 | 4
This risk assessment form must be completed and submitted with every Research and Innovation Office
(RIO) Proposal Approval Form for Research & Commercial Proposal authorisation.
[10 empty] | Signed : Principal Investigator |  |  | Date:
[10 empty] | Signed : Associate Dean of Research |  |  | Date:
[10 empty] | Signed : School Dean / Vice-Dean (required if Project value greater than £50k) |  |  | Date:
(The above signatures are not required for a PGR risk register. The signatures obtained at RDC milestones, eg RDC1,
where the risk register is required to be submitted, suffice to cover the approval of the student's risk register.)

## Notes to aid Completion
Notes on Completion of Project Risk Register
Notes per Highlighted Cells/Columns on Example Risk Register |  | Additional Points to note while completing a Risk Register
A | Insert total value of Project Funding or Projected Income for full life of project | 1 | The Example Risk Register is provided to highlight some key risks that would consistently be expected to be reflected in a Risk Register. These are provided purely for example purposes and it is expected that these are used as guidelines and not just copied into the relevant Project Risk Register. Each Project Risk Register should be compiled based on the Risks specific to the individual project.
B | Delete the shaded row with instructions, list the Risks sequentially from 1. Delete any template rows that are unused | 2 | There is no right or wrong number of Risks but we would generally expect a minimum of five and a maximum of fifteen depending on the project.
C | Provide a brief succinct description of the Risk identified | 3 | The Gross Risk is the theoretical risk without any of the existing controls, the Residual Risk is the actual risk given the controls in place and, therefore, should be lower than the Gross Risk. The Residual Risk can never be higher than the Gross Risk and if it is the same as the Gross Risk then we are indicating that there are either no mitigating actions or controls or that any controls are having no impact.
D | Input a Gross Likelihood score per the 4x4 Matrix grading of Minor to Major - Drop down menu provided. The Gross Risk is the assumed Risk without any of the controls in place or existing mitigating actions | 4 | The Risk Register should be a live document and reviewed regularly in line with the lifetime and key milestones of the project.
E | Input a Gross Impact score per the 4x4 Matrix grading of Unlikely to Certain - Drop down menu provided. The Gross Risk is the assumed Risk without any of the controls in place or existing mitigating actions | 5 | To delete/add rows, highlight the row, right click and choose either Insert or Delete.
F | Cell calculates automatically based on Likelihood and Impact Scores | 6 | When inputting into a cell and wanting a new line within the cell, hold down the Alt key and then hit Return
G | Provide details of the existing controls and actions which are in place to reduce the likelihood or impact of the Risk identified | 7 | When reviewing the Risk Register it is expected that over time the Actions Planned should move into Controls in Place/Mitigating Actions once completed and contribute towards a potentially lower Residual Risk score.
H | Input a Residual Likelihood score per the 4x4 Matrix grading of Minor to Major - Drop down menu provided. The Residual Risk is the assumed Risk after taking account of all controls in place or existing mitigating actions
I | Input a Residual Impact score per the 4x4 Matrix grading of Minor to Major - Drop down menu provided. The Residual Risk is the assumed Risk after taking account of all controls in place or existing mitigating actions
J | Cell calculates automatically based on Likelihood and Impact Scores
K | Provide details of any Early Warning Mechanisms which would indicate the risk has materialised and any Actions Planned to mitigate against the Risk. The Residual Risk score should not take these planned actions into account, however, once they are in place, they would be assumed to move into the Mitigating Actions column and contribute to reducing the Residual Risk score
L | Provide details of any key timelines/dates in relation to the noted Actions Planned
M | Provide details of actions completed since last review - have these now been moved to Controls in Place/Mitigating Actions and should the Risk score change?
N | Risk Owner - Should be one individual where possible

## Generic Example Risk Register
GLASGOW CALEDONIAN UNIVERSITY | [9 empty] | SCHOOL/DEPARTMENT |  | GSBS/EBE/SHLS/GCU London/SWBE/YUNUS etc.
[10 empty] | PROJECT NAME |  | Example Research Project
PROJECT RISK REGISTER | [9 empty] | PROJECT VALUE |  | A
[10 empty] | OVERALL RESIDUAL PROJECT RISK |  |  |  | B
B | C |  |  | D | E | F | G | H | I | J | K | L | M | N
No. | SPECIFIC RISK |  |  | IMPACT (i.e. severity) | LIKELIHOOD | GROSS RISK SCORE AS PER MATRIX (1 - 16) | MITIGATION ACTIONS, PROCEDURES/CONTROLS IN PLACE | IMPACT (i.e. severity) | LIKELIHOOD | RESIDUAL RISK SCORE AS PER MATRIX (1 - 16) | 1. EARLY WARNING MECHANISMS 2. ACTIONS PLANNED | Timeline | Completed Actions | RISK OWNER
| Provide clear detail of the project risk, and then using the table below evaluate the impact and likelihood of this risk without any controls in place. |  |  | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List all mitigating actions, procedures and controls which will then impact on the gross risk score to create a revised residual risk score. | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List early warning mechanisms and other planned future actions which enhance the management of this risk, providing timelines where appropriate. | Key Milestone dates for any material events or actions planned | Note Actions completed since last Risk Register review | Name. Should be one individual
1 | Reputational risk that GCU provides an incorrect Research conclusion that is based on flawed assumptions or incorrect/incomplete data |  |  | Major | Probable | 1 | • Peer review of data sample techniques and project conclusions • Appropriately qualified staff in position | Major | Unlikely | 4 | Early Warning Mechanisms • Issues collecting appropriate data samples • Departure of key personnel from project • Partner institutions missing deadlines and submitting incomplete data Actions Planned • Regular communication with funding body to highlight any concerns with project delivery |  |  | PI
2 | Risk that GCU does not meet the contracted deliverables or timelines in line with agreed Project parameters |  |  | Major | Certain | 16 | • Peer review of data sample techniques and project conclusions • Appropriately qualified staff in position • Project timeline and milestones agreed with funder • Regular project meetings with all stakeholders to review progress against agreed timelines | Major | Unlikely | 4 | Early Warning Mechanisms • Recruitment cycle factored into project timelines • Partner institutions missing deadlines and submitting incomplete data Actions Planned • Risk of third party providing key data highlighted to funder as impacting timelines |  |  | PI
3 | Risk that GCU as Lead partner fails to manage the risks and outputs of other contributing partner institution |  |  | Major | Probable | 12 | • Signed agreements with Partner Institutions outlining agreed outputs and timelines • Regular communication with Partners to highlight potential risks/issues that have arisen • Diligence carried out on key partners where appropriate | Significant | Unlikely | 2 | Early Warning Mechanisms • Partner Institution departing from project • Partner institutions missing deadlines and submitting incomplete data Actions Planned • Risk of third party providing key data highlighted to funder as impacting timelines |  |  | PI
4 | Risk that key personnel leave project with insufficient handover or no alternative personnel/skills in place |  |  | Major | Possible | 8 | • Contingency plans in place if key personnel leave Institution or fall ill • Appropriately qualified staff in position | Serious | Possible | 6 | Early Warning Mechanisms • Absence of key personnel • Inability to recruit appropriately qualified staff Actions Planned •Agree any contingency plans and impact on timelines with key stakeholders |  |  | PI
5 | Risk that GCU is unable to collect sufficient sample data to meet the project deliverables |  |  | Major | Possible | 8 | • Research parameters outlined in project contract with appropriate mitigating procedures in place • Signed contract/agreements in place with key third party data providers • Diligence carried out on key partners where appropriate | Significant | Possible | 4 | Early Warning Mechanisms • Third party partners missing agreed deadlines Actions Planned • Regular communication with funders and stakeholders to highlight any issues with agreed timelines or outputs |  |  | PI
6 | Risk that GCU does not recover all of agreed funding due to non-approved expenditure or spend outwith the terms of the funding, leading to an overall deficit to the Budgeted project contribution |  |  | Major | Possible | 8 | • Agreed funding contract in place • Project Budget approved through RIE and Finance • Appropriate procurement procedures in place to ensure purchases are in line with agreed expenditure • All reporting requirements factored into Project plan and responsibilities agreed | Significant | Possible | 4 | Early Warning Mechanisms • Deviation from agreed budgeted expenditure highlighted by Finance Actions Planned • Regular review of Project actual spend v Budgets |  |  | PI
7 | Risk of data breach and sensitive information not being treated in line with legislative requirements |  |  | Major | Probable | 12 | • GCU Data Management and Information Security Policy • All project staff members appropriately trained in Information Security and Data Management • All non GCU project partners with access/control over data are covered by appropriate compliance procedures to ensure equal standards with GCU data management and Information Security | Major | Unlikely | 4 | Early Warning Mechanisms • Data sharing issues highlighted during contractual negotiations with project partners Actions Planned • Regular communication to personnel and partners to reiterate data management compliance procedures |  |  | PI
9 | Specific Project Risk |  |  | F: 0; OVERALL RESIDUAL PROJECT RISK J: 0
10 | Specific Project Risk |  |  | F: 0; OVERALL RESIDUAL PROJECT RISK J: 0
8 | Health and Safety Risk to individuals in relation to foreign travel/work carried out at 3rd party premises |  |  | Serious | Probable | 9 | • GCU Health and Safety Policy • GCU travel Risk Assessment • Appropriate Diligence carried out on any 3rd party contractors/partners to assure appropriate insurance and risk assessments are in place. | Serious | Unlikely | 3 | Early Warning Mechanisms • Data sharing issues highlighted during contractual negotiations with project partners Actions Planned • Regular communication to personnel and partners to reiterate data management compliance procedures |  |  | PI
Impact
|  | 0 | Minor | D: Significant; E: Serious; F: Major
| Likelihood | Certain | 4 | D: 8; E: 12; F: 16
|  | Probable | 3 | D: 6; E: 9; F: 12
|  | Possible | 2 | D: 4; E: 6; F: 8
|  | Unlikely | 1 | D: 2; E: 3; F: 4
This risk assessment form must be completed and submitted with every Research, Innovation
and Enterprise (RIE) Proposal Approval Form for Research & Commercial Proposal authorisation.
[10 empty] | Signed : Principal Investigator |  |  | Date:
[10 empty] | Signed : Associate Dean of Research |  |  | Date:
[10 empty] | Signed : Executive Dean / Head of Function |  |  | Date: